PERSAT FINANCE

10-Week Roadmap: MVP to 1,000 Users

Version 2 — Global, Single Oracle, Dual-Path Model

Persat Labs Limited  |  Version 2.0 — Global  |  2026

Read This Before The Roadmap

Two things changed since the first version of this plan, and both are reflected throughout: the architecture simplified in one place (a single BTC/USD oracle replaces the earlier dual-oracle design, since loans now settle in USDC/USDT rather than a local-currency stablecoin), and it expanded in another (an open marketplace now sits alongside the private deal-link path, requiring real new frontend and backend scope). The net effect is not neutral — read the Risks section at the end honestly before treating this as a fixed 10-week guarantee.

What “1,000 Users” still means 1,000 people who have connected a wallet and meaningfully interacted with Persat Finance on testnet — not 1,000 people moving real Bitcoin and real stablecoins. Real-money mainnet activity follows a completed external audit and is out of scope for this window.

What “Complete MVP” now means All eight core Solana programs live on testnet (including the Deal Registry's public/private visibility modes), the marketplace frontend fully functional alongside the direct-deal frontend, all four security audit passes clean, and a non-technical first-time user able to complete a full loan — through either path — unassisted.

Phase Overview

| Phase | Weeks | Focus |
| --- | --- | --- |
| Phase 1 — Foundation & Core Build | 1–4 | Brand/global positioning live, core Solana programs including dual-mode Deal Registry |
| Phase 2 — Complete Build & Audit | 5–6 | Remaining programs, Pass 1 & 2 audits, full frontend — direct-deal AND marketplace |
| Phase 3 — Testnet & Closed Beta | 7 | Public testnet deployment, Pass 3 audit, closed beta (direct-deal path only) |
| Phase 4 — Public Launch | 8 | Pass 4 adversarial audit, public testnet opens, marketplace opens publicly |
| Phase 5 — Growth Sprint | 9–10 | Push toward 1,000 users across both paths |

WEEK 1 Lock the Architecture, Global Brand Foundation

Engineering

- Confirm single-oracle architecture (BTC/USD only) and the Asset Whitelist Registry design covering both collateral (tBTC, zBTC) and loan-currency assets (USDC, USDT)

- Set up Anchor/Solana dev environment, devnet wallets, CI pipeline

- Begin coding the Deal Registry program, including its public/private visibility flag from the start — this avoids a costly retrofit later

Content & Brand

- Finalize global brand copy — no country or currency-specific language anywhere

- Re-open the waitlist with global positioning; migrate existing signups with a clear, honest note explaining the evolution

Content to publish this week

- Announcement: introducing Persat Finance's global positioning and the upcoming marketplace

Week 1 checkpoint

- Single-oracle and dual-mode Deal Registry design locked. Global brand live. Waitlist re-opened.

WEEK 2 Core Programs — Registry & Whitelist

Engineering

- Complete Deal Registry program with unit tests, including propose_deal (public and private modes), confirm_deal, cancel_deal

- Build the Asset Whitelist Registry — add_asset_type, is_accepted, covering both collateral and loan-currency tokens

- Integrate tBTC, zBTC, USDC, USDT addresses into the whitelist on devnet

Content to publish this week

- Educational thread: what a Bitcoin bridge is, in plain language

- Short piece: why Persat Finance uses two bridges, referencing the Botanix lesson directly

Week 2 checkpoint

- Deal Registry (both modes) complete and tested. Whitelist Registry live with all four assets on devnet.

WEEK 3 Core Programs — Escrow & Oracle

Engineering

- Build the Escrow Vault program: deposit_collateral, release_collateral, seize_collateral

- Build the single PriceOracle adapter (BTC/USD only) — integrate Pyth or Switchboard

- Cross-program invocation testing between Deal Registry, Whitelist Registry, Escrow Vault

Content to publish this week

- Explainer video: a direct deal walkthrough, using the How It Works guide's example

- Begin press outreach with the pivot-and-global story as the angle

Week 3 checkpoint

- Escrow Vault integrated with Registry programs. Single oracle functional on devnet with live BTC/USD data.

WEEK 4 Core Programs — Loan Lifecycle & Liquidation

Engineering

- Build the Loan Lifecycle / Payment Program: activate_loan, make_payment, check_payment_status, flag_default

- Build the Liquidation Engine: evaluate_position, execute_partial_liquidation, execute_full_liquidation

- First full manual dry run: propose → confirm → fund → activate → repay → release, end to end on devnet

Content to publish this week

- Thread: what happens if a payment is missed — explained honestly, ahead of launch

- Build-in-public update with real devnet transaction evidence

Week 4 checkpoint

- First full loan lifecycle executed successfully end to end on devnet, direct-deal path.

WEEK 5 Remaining Programs & Security Audit Pass 1

Engineering

- Build the Fee & Treasury Program and Governance Program

- All core programs now functionally complete, including both Deal Registry modes

- Begin Security Audit Pass 1 — unit test coverage across all programs, 95%+ target. Fix all issues before proceeding.

Content to publish this week

- Milestone post: core infrastructure complete, entering the audit phase — explain what the four-pass process actually checks

Week 5 checkpoint

- All core programs complete. Pass 1 underway, critical/high issues resolved by week end.

WEEK 6 Security Audit Pass 2 & Full Frontend Build

Engineering — this week carries the added marketplace scope

- Complete Security Audit Pass 2 — fuzz testing, 10,000+ iterations on all financial calculations

- Build the direct-deal frontend: create deal, generate/share link, claim, fund, manage, repay

- Build the marketplace frontend: browse listings, post a listing, propose against a listing, review incoming proposals — all with structured terms only, no free-text fields, per the Testnet Flow spec

- Connect both frontends to live devnet contracts

Honest flag This week now covers meaningfully more frontend surface than the original plan. If it doesn't fully complete within the week, the marketplace frontend is what should slip into Week 7 — not the security audit, and not the direct-deal path, which the Week 7 closed beta depends on.

Week 6 checkpoint

- Pass 2 complete. Direct-deal frontend fully functional. Marketplace frontend functional or explicitly flagged as spilling into Week 7.

WEEK 7 Public Testnet Deployment & Closed Beta

Engineering

- Deploy all programs to Solana public testnet

- Run Security Audit Pass 3 — full integration testing on the live deployment, every scenario documented with a transaction signature, covering both Deal Registry modes

- Finish marketplace frontend here if it spilled over from Week 6

Users & Beta

- Onboard 15–20 closed-beta users through the direct-deal path only — the marketplace stays closed until Week 8, so the first public listings launch with at least some real completed-loan history behind them, not zero

Week 7 checkpoint

- Testnet live. Pass 3 clean. 15–20 closed-beta users have each completed a direct deal. Marketplace built and ready, not yet public.

WEEK 8 Adversarial Audit & Public Launch — Marketplace Opens

Engineering

- Run Security Audit Pass 4 — adversarial self-attack, now explicitly including marketplace-specific vectors: fake listings, proposal spam, attempts to extract contact info or move negotiation off-platform through the structured-terms fields

- Fix any successful exploit; repeat Pass 3 and 4 if contract behavior changes

Users & Growth

- Open public testnet access to the full waitlist

- Open the marketplace publicly for the first time — the closed-beta users' completed loans give early listings real history to display

- Activate referral incentives; publish press outreach from Week 3

Week 8 checkpoint

- Pass 4 clean, zero unresolved critical findings. Public testnet and public marketplace both live simultaneously.

WEEK 9 Growth Sprint I

Engineering

- Monitor both paths under real load; fix UX or reliability issues surfaced by real usage. No new features.

Users & Growth

- Daily community engagement across global crypto and Bitcoin communities — not limited to any single regional group

- Track which path (direct-deal vs marketplace) is driving more completed loans and double down on whichever is converting

Content to publish this week

- Real numbers: completed loans so far, split by path, published transparently

Week 9 checkpoint

- Running user count tracked daily, by path. Best-performing acquisition channel identified.

WEEK 10 Growth Sprint II — Push to 1,000

Engineering

- Continue stability monitoring and rapid bug response

- Begin drafting the post-MVP roadmap: mainnet audit scoping, bridge-free Bitcoin-native escrow research (per the competitive analysis finding on Firefish and Hodl Hodl), real fee model finalization

Users & Growth

- Concentrated push on the best-performing channel from Week 9

- Time-boxed incentive if short of 1,000 by mid-week

Content to publish this week

- The 1,000-user milestone announcement, with an honest split of direct-deal vs marketplace activity

- Retrospective piece: what changed since the original Nigeria-specific, Botanix-based version of this product, and why — this becomes primary material for seed conversations

Week 10 checkpoint — End of Roadmap

- MVP complete across both paths, all four audits clean, 1,000+ testnet users reached.

Risks To This Timeline

- The marketplace is the single biggest addition to scope since the last version of this plan. It touches Week 6 (frontend), Week 7 (contingency buffer), and Week 8 (public opening, expanded adversarial audit surface) simultaneously. If any one of these slips, the whole chain shifts right — plan for that explicitly rather than being surprised by it.

- A marketplace with zero completed-loan history at public launch would undermine the trust signal the whole feature depends on. The Week 7 closed-beta-only, Week 8 marketplace-opens sequencing exists specifically to avoid this — do not open the marketplace earlier than planned even under schedule pressure.

- Firefish and Hodl Hodl have spent years refining what safe marketplace negotiation looks like. Persat Finance is adopting the pattern quickly. Expect real early friction — confusing edge cases, users trying to work around the no-free-text rule — that a mature competitor has already smoothed out.

- The single-oracle simplification is a genuine risk reduction — one fewer feed to keep fresh, one fewer failure mode — but it introduces a new, smaller risk: reliance on USDC/USDT holding their peg. This is accepted as a reasonable MVP-stage trade-off, not an oversight, per the Technical Architecture paper.

Persat Finance  |  Persat Labs Limited  |  10-Week Roadmap  |  persat.ng@gmail.com